## Cover Sheet
ASSIGNMENT 1
DO INITIAL VERSION OF PERSONAL WBS
CSE 6329
Software Metrics and Quality Engineering
Spring, 2018
Name | Somanahalli Muralidhara, Karthik
ID | 1001520125
Points
(/10) Correct Format, including name on top, totals, etc.
(/50) Reasonable list of tasks for each assignment
(/40) Reasonable estimates, actual and earned hours.
(100) Total Assignment Grade
Comments from Grader
1

## Instructions
Instructions for Weekly WBS Entries
General Rules:
1: Cells with a white background are cells in which you may put a number or a task name at the appropriate time.
Some of these cells will change color when you put something there.
2: Row 7 contains the headers for the many rows that follow. These row headers are color coded:
|  | If a cell has a header that is |  |  | light blue | it means you should consider entering data there each week.
|  | If a cell has a header that is |  |  | beige | it means you should enter data there once and not change it later.
|  | If a cell has a header that is |  |  | light green | it means you should enter task numbers and names there once.
|  | If a cell has a header that is |  |  | yellow | it means it contains a formula that you should not change.
Note: you might add new rows in the main body of the WBS (see SOW for details)
2: Cells with a colored background usually contain formulas that you should not change unless you are extending
the length of the course (which you may only do with the instructor's permission).
3: You may insert rows as needed to accommodate all of the tasks that you plan to do for the course.
(Use the spare tasks near the bottom to preserve the correct format and formulas.)
4: You should study every formula and every graph and understand what it is and why. This may be on an exam.
Step 1 - Enter hours worked each week
At the end of each week, fill in hours worked on each task, as follows:
(hours may be entered in whole hours, such as 2, or in tenths of an hour, such as 1.3)
For each task:
If you did no work on that task, do nothing.
If you worked on that task during the past week:
Enter total hours worked on the task in the column corresponding to the current week (column U through AJ).
Cell should change color when you enter a non-zero value.
Enter total hours of work remaining on the task in column E:
If the task is complete, enter 0 hours remaining.
The total hours remaining is your best current estimate, which may differ from what was originally estimated.
Step 2: Check for errors
Review all totals and numbers and make sure everything seems correct.
Make corrections as necessary
If the graphs (charts) look strange, something is wrong. Figure out what's wrong and fix it.
Step 3: Record Estimated Hours Remaining at end of current week
Copy the "total estimated hours remaining" (bottom of column E) to estimated hours remaining cell for current week
Cell will change color
This will update the burndown and burnup charts
Step 4: Update Earned Value
The hours earned this week row for the current week (near the bottom) should start off with blank or 0.
For each task that has completed during the current week:
Find the originally estimated hours for that task and add it to the hours earned this week for the current week
When done, this total will be the earned value for the week and will update the earned value chart accordingly.

## WBS
|  | PWBS | [10 empty] | Planned Effort |  | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 |  | 147
Not Started | 2018 Spring | CSE 6329-002 | Schedule | [9 empty] | Cumulative Plan (PV) |  | 10.5 | 21 | 31.5 | 42 | 52.5 | 63 | 73.5 | 84 | 94.5 | 105 | 115.5 | 126 | 136.5 | 147
In Progress | Somanahalli Muralidhara,Karthik | [11 empty] | Estimated Effort Remaining | 147 | 136.5 | 126 | 115.5 | 105 | 94.5 | 84 | 73.5 | 63 | 52.5 | 42 | 31.5 | 21 | 10.5 | 0
Complete | Actual Results |  |  | Estimates |  | WBS | [8 empty] | Actual Hours Worked and Earned
Status | Estimated Hours Remaining | Actual Hours So Far | Actual Completion Week | Estimated Hours of Effort | Planned Completion Week | Task # |  | Task Description |  |  |  |  | Week Ending >> |  | 2018-01-26 | 2018-02-02 | 2018-02-09 | 2018-02-16 | 2018-02-23 | 2018-03-02 | 2018-03-09 | 2018-03-16 | 2018-03-23 | 2018-03-30 | 2018-04-06 | 2018-04-13 | 2018-04-20 | 2018-04-27 | insert new column here | Total Hours Worked
[6 empty] | 10000 | A1 - Develop PWBS
[6 empty] | 11000 |  | Read and Analyze A1 SOW for PWBS | [21 empty] | 0
Complete | 0 | 2 |  | 2 |  | 11100 |  |  | List tasks to be performed |  | the tasks needed to be done |  |  |  | 2018-01-26: 2 |  | 2
Complete | 0 | 1.5 |  | 2 |  | 11200 |  |  | Estimate hours required for each task | [20 empty] | 1 | bar: 2018-01-26
Complete | 0 | 1 |  | 0.8 |  | 11300 |  |  | Break into smaller sub-tasks as required |  |  | tasks into subtasks | [17 empty] | 1 | bar: 2018-01-26
Complete | 0 | 0.8 |  | 1 |  | 11400 |  |  | Modify template to add tasks and correct formulas/coloring | [5 empty] | 2018-01-26: 0.8 |  | 0.8
Complete | 0 | 0.5 |  | 0.5 |  | 11500 |  |  | Record estimated hours in Estimated Hours of Effort column | [5 empty] | 2018-01-26: 0.6 |  | 0.6
[6 empty] | 12000 |  | Read and Analyze A2 SOW
Complete | 0 | 2 |  | 2 |  | 12100 |  |  | List tasks to be performed | [5 empty] | 2018-01-26: 2 |  | 2
Complete | 0 | 0.8 |  | 1 |  | 12200 |  |  | Estimate hours required for each task | [5 empty] | 2018-01-26: 0.8 |  | 0.8
Complete | 0 | 1 |  | 1.2 |  | 12300 |  |  | Break into smaller sub-tasks as required | [20 empty] | 1 | bar: 2018-01-26
Complete | 0 | 0.6 |  | 0.6 |  | 12400 |  |  | Modify template to add tasks and correct formulas/coloring | [5 empty] | 2018-01-26: 0.6 |  | 0.6
Complete | 0 | 0.6 |  | 0.6 |  | 12500 |  |  | Record estimated hours in Estimated Hours of Effort column | [5 empty] | 2018-01-26: 0.6 |  | 0.6
[6 empty] | 13000 |  | Read and Analyze A3 SOW
Complete | 0 | 2 |  | 2 |  | 13100 |  |  | List tasks to be performed | [5 empty] | 2018-01-26: 2 |  | 2
Complete | 0 | 1 |  | 1 |  | 13200 |  |  | Estimate hours required for each task | [20 empty] | 1 | bar: 2018-01-26
Complete | 0 | 1 |  | 1.5 |  | 13300 |  |  | Break into smaller sub-tasks as required | [20 empty] | 1 | bar: 2018-01-26
Complete | 0 | 0.6 |  | 0.6 |  | 13400 |  |  | Modify template to add tasks and correct formulas/coloring | [5 empty] | 2018-01-26: 0.6 |  | 0.6
Complete | 0 | 1 |  | 1 |  | 13500 |  |  | Record estimated hours in Estimated Hours of Effort column | [20 empty] | 1 | bar: 2018-01-26
[6 empty] | 14000 |  | Read and Analyze A4 SOW
Complete | 0 | 2 |  | 2 |  | 14100 |  |  | List tasks to be performed | [5 empty] | 2018-01-26: 2 |  | 2
Complete | 0 | 1.2 |  | 1.4 |  | 14200 |  |  | Estimate hours required for each task | [5 empty] | 2018-01-26: 1.2 |  | 1.2
Complete | 0 | 1.3 |  | 1.3 |  | 14300 |  |  | Break into smaller sub-tasks as required | [5 empty] | 2018-01-26: 1.3 |  | 1.3
Complete | 0 | 1 |  | 1 |  | 14400 |  |  | Modify template to add tasks and correct formulas/coloring | [20 empty] | 1 | bar: 2018-01-26
Complete | 0 | 0.6 |  | 0.6 |  | 14500 |  |  | Record estimated hours in Estimated Hours of Effort column | [5 empty] | 2018-01-26: 0.6 |  | 0.6
Complete | 0 | 1 |  | 1 |  | 15000 |  | Enter Actual and Earned Hours for week ending 1/27 | [21 empty] | 1 | bar: 2018-01-26
Complete | 0 | 0.2 |  | 1 |  | 15100 |  | Submit A1 (Draft) | [6 empty] | 2018-01-26: 0.2 |  | 0.2
Complete | 0 | 2 |  | 2 |  | 16000 |  | Review comments from TA/Instructor and Correct Mistakes | [6 empty] | 2018-02-09: 2 |  | 2
Complete | 0 | 2 |  | 2 |  | 17000 |  | Submit A1-Interim | [6 empty] | 2018-02-09: 2
[6 empty] | 18000 |  | Make Weekly Updates to Actual and Earned Hours in PWBS
Complete | 0 | 1 |  | 1 |  | 18100 |  |  | Record hours worked for week ending |  |  |  | 2018-01-26 | [16 empty] | 1 | bar: 2018-01-26
Complete | 0 | 1 |  | 1 |  | 18200 |  |  | Record hours worked for week ending |  |  |  | 2018-02-02 | [16 empty] | 1 | bar: 2018-02-02
In Progress | 1 | 1 |  | 1 |  | 18300 |  |  | Record hours worked for week ending |  |  |  | 2018-02-09 | [16 empty] | 1 | bar: 2018-02-09
Not Started | 1 | 0 |  | 1 |  | 18400 |  |  | Record hours worked for week ending |  |  |  | 2018-02-16 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 18500 |  |  | Record hours worked for week ending |  |  |  | 2018-02-23 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 18600 |  |  | Record hours worked for week ending |  |  |  | 2018-03-02 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 18700 |  |  | Record hours worked for week ending |  |  |  | 2018-03-09 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 18800 |  |  | Record hours worked for week ending |  |  |  | 2018-03-16 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 18900 |  |  | Record hours worked for week ending |  |  |  | 2018-03-23 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 18910 |  |  | Record hours worked for week ending |  |  |  | 2018-03-30 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 18920 |  |  | Record hours worked for week ending |  |  |  | 2018-04-06 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 18930 |  |  | Record hours worked for week ending |  |  |  | 2018-04-13 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 18940 |  |  | Record hours worked for week ending |  |  |  | 2018-04-20 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 18940 |  |  | Record hours worked for week ending |  |  |  | 2018-04-27 | [16 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 19000 |  | Submit Final PWBS | [21 empty] | 0
[6 empty] | 20000 | A2
|  | 0 |  |  |  | 21000 |  | Design and implement a Defect Recording and Analysis tool | [21 empty] | 0
Not Started | 2 | 0 |  | 2 |  | 21100 |  |  | Record the defected data | [20 empty] | 0
Not Started | 1.8 | 0 |  | 1.8 |  | 21200 |  |  | Help with refinement and analysis of the data | [20 empty] | 0
Not Started | 2 | 0 |  | 2 |  | 21300 |  | Fill in new rows as required | Generate various graphs illustrating measures | [20 empty] | 0
|  | 0 |  |  |  | 22000 |  | POST RELEASE QUALITY FOR PRODUCT ZD | [21 empty] | 0
Not Started | 1.6 | 0 |  | 1.6 |  | 22100 |  |  | Analysis Tool Description | [20 empty] | 0
|  | 0 |  |  |  | 22200 |  |  | Post-release Quality Average for all products, by development process | [20 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 22210 |  |  |  | An overview of the measure and graph | [19 empty] | 0
Not Started | 2 | 0 |  | 2 |  | 22220 |  |  |  | Sample graph using data from worksheets | [19 empty] | 0
[6 empty] | 22230 |  | Post-release Quality Average for all products, normalized by size
Not Started | 0.3 | 0 |  | 0.3 |  | 22231 |  |  |  |  | General discussion of what the measure and graph tells | [18 empty] | 0
Not Started | 1 | 0 |  | 1 |  | 22232 |  |  |  |  | Specific discussion of sample graphs | [18 empty] | 0
Not Started | 2 | 0 |  | 2 |  | 22233 |  |  |  |  | The procedure by which data are refined and the graph is produced | [18 empty] | 0
[6 empty] | 22234 |  |  | Post-release Quality Average for all products, by programming language
Not Started | 1 | 0 |  | 1 |  | 22235 | [5 empty] | An Overview of the measure and graph
Not Started | 1.5 | 0 |  | 1.5 |  | 22236 | [5 empty] | Sample graph using data from worksheets
[6 empty] | 22237-1 |  |  | Post-release quality HISTORY
Not Started | 1 | 0 |  | 1 |  | 22237 | [5 empty] | An Overview of the measure and what graph tells
Not Started | 1.5 | 0 |  | 1.5 |  | 22238 | [5 empty] | Specific discussion of graph samples
Not Started | 1.5 | 0 |  | 1.5 |  | 22239 | [5 empty] | ANALYSIS
[6 empty] | 22240-1 |  |  | Graph of Your Choice
Not Started | 1.2 | 0 |  | 1.2 |  | 22244 | [5 empty] | Selection of the graph
Not Started | 1.6 | 0 |  | 1.6 |  | 22248 | [5 empty] | Analysis of the graph
Not Started | 1 | 0 |  | 1 |  | 22249 | [5 empty] | specific discussion related to the graph
[6 empty] | 22250-1 |  |  | Current Quality Total
Not Started | 1.7 | 0 |  | 1.7 |  | 22250 | [5 empty] | Analysis of the graph
Not Started | 1.5 | 0 |  | 1.5 |  | 22251 | [5 empty] | Interpretation of what the graph describes
Not Started | 1.3 | 0 |  | 1.3 |  | 22252 | [5 empty] | Drawing Coclusions related to the graph
Not Started | [5 empty] | 22253 |  |  | Current quality total normalised by size of active product releases
Not Started | 1.2 | 0 |  | 1.2 |  | 22254 | [5 empty] | Analysis
Not Started | 1 | 0 |  | 1 |  | 22255 | [5 empty] | Normalisation
Not Started | 1.2 | 0 |  | 1.2 |  | 22256 | [5 empty] | Interpretation
[6 empty] | 22257 |  |  | Current Quality Total, normalized by number of currently active products
Not Started | 1.3 | 0 |  | 1.3 |  | 22258 | [5 empty] | Analysis
Not Started | 1.4 | 0 |  | 1.4 |  | 22259 | [5 empty] | Normalisation
Not Started | 1.2 | 0 |  | 1.2 |  | 22260 | [5 empty] | Interpretation
Not Started | 1.4 | 0 |  | 1.4 |  | 25000 |  |  | Review with teammate and Submit A2 | [20 empty] | 0
[6 empty] | 30000 | A3
[6 empty] | 31000 |  | Phase 1
Not Started |  | 0 |  |  |  | 31100 |  |  | Main Program
Not Started | 1.5 | 0 |  | 1.5 |  | 31110 |  |  |  | Produce a flowgraph of the main program
Not Started | 2 | 0 |  | 2 |  | 31120 |  |  |  | Compute the cyclomatic complexity of the main program
[6 empty] | 31200 |  |  | Function
Not Started | 2 | 0 |  | 2 |  | 31210 |  |  |  | Write a C function that satisfies the requirements indicated in appendix
Not Started | 2 | 0 |  | 2 |  | 31220 |  |  |  | Produce a flowgraph of the function
Not Started | 2 | 0 |  | 2 |  | 31230 |  |  |  | Compute the cyclomatic complexity of the function
Not Started | 1 | 0 |  | 1 |  | 31300 |  |  | Review with teamate and submit A3
[6 empty] | 32000 |  | Phase 2
[6 empty] | 32100 |  |  | For each function;running total of all three
Not Started | 1.3 | 0 |  | 1.3 |  | 31110 |  |  |  | Review the function and note any errors
Not Started | 1.2 | 0 |  | 1.2 |  | 31120 |  |  |  | Produce a flowgraph of the function
Not Started | 1.4 | 0 |  | 1.4 |  | 31130 |  |  |  | Determine the Cyclomatic Complexity of the Function
Not Started | 1.6 | 0 |  | 1.6 |  | 31140 |  |  |  | Turn in a Word file containing the flowgraph
Not Started | 1 | 0 |  | 1 |  | 33000 |  | Review with teamate and submit A3 phase 2
[6 empty] | 40000 | A4
[6 empty] | 41000 |  | Read and Analyze A4 SOW
Not Started | 2 | 0 |  | 2 |  | 41100 |  |  | Identify two CTQs that measure the important factors to the customer
[6 empty] | 41200 |  |  | Explain the process flow and produce a swim lane diagram
Not Started | 1.6 | 0 |  | 1.6 |  | 41210 |  |  |  | Examine the handouts to identify all the organizations involved
Not Started | 2 | 0 |  | 2 |  | 41220 |  |  |  | Determine the order in which things happen and the dependencies
Not Started | 1 | 0 |  | 1 |  | 41230 |  |  |  | Use the information gathered to produce a swim lane diagram
Not Started | 1.5 | 0 |  | 1.5 |  | 41240 |  |  |  | Analyze the diagram to determine places where there are delays
[6 empty] | 41300 |  |  | Use two or more of the techniques to analyze the various possible
Not Started | 1.2 | 0 |  | 1.2 |  | 41310 |  |  |  | Discuss the causes in the order in which tthey should be addressed
Not Started | 1.1 | 0 |  | 1.1 |  | 41320 |  |  |  | Determine that the root cause is in another part of the process
Not Started | 2 | 0 |  | 2 |  | 41400 |  |  | Produce a cause map (causal model) showing all factor
Not Started | 2 | 0 |  | 2 |  | 41500 |  |  | Identify the three root causes and, for each, produce a flow diagram
Not Started | 2 | 0 |  | 2 |  | 41600 |  |  | Explain your recommendations, based on your assessment and analysi
Not Started | 1.3 | 0 |  | 1.3 |  | 41700 |  |  | Discuss with teamate
|  | 0 |  |  |  | 50000 | E1 - Study for Midterm Exam | [22 empty] | 0
Not Started | 2 | 0 |  | 2 |  | 51000 |  |  |  | Study module 1,2 and 3
Not Started | 2 | 0 |  | 2 |  | 52000 |  |  |  | Study module 4,5, & 6
Not Started | 2 | 0 |  | 2 |  | 53000 |  |  |  | Study module 7,8 &9
Not Started | 2 | 0 |  | 2 |  | 54000 |  |  |  | Study module 10,11,& 12
Not Started | 2 | 0 |  | 2 |  | 55000 |  |  |  | Study module 13,14 and 15
Not Started | 2 | 0 |  | 2 |  | 56000 |  |  |  | Study module 16,17 and 18
Not Started | 2 | 0 |  | 2 |  | 57000 |  |  |  | Study module 19 &20
Not Started | 2 | 0 |  | 2 |  | 60000 | E2 - Study for Final Exam
Not Started | 2 | 0 |  | 2 |  | 61000 |  |  |  | Prepare for module 1 and 2
Not Started | 2 | 0 |  | 2 |  | 62000 |  |  |  | Prepare for Module 3 and 4 and 5
Not Started | 2 | 0 |  | 2 |  | 63000 |  |  |  | Prepare for Module 6 , 7 and 8
Not Started | 2 | 0 |  | 2 |  | 64000 |  |  |  | Prepare for Module 9 , 10 , 11 and 12
Not Started | 2 | 0 |  | 2 |  | 65000 |  |  |  | Study module 13,14 and 15
Not Started | 2 | 0 |  | 2 |  | 66000 |  |  |  | Study module 16,17 and 18
Not Started | 2 | 0 |  | 2 |  | 67000 |  |  |  | Study module 19 &20 | [19 empty] | 0
Spare Task Rows - For use in Inserting New Tasks and Sub-Tasks
Spare Parent Task - Top Level
Spare Parent Task - Second Level
Spare Parent Task - Third Level
Not Started |  | 0 | [5 empty] | Spare Sub-Task - Second Level | [21 empty] | 0
Not Started |  | 0 | [6 empty] | Spare Sub-Task - Third Level | [20 empty] | 0
Not Started |  | 0 | [7 empty] | Spare Sub-Task - Fourth Level | [19 empty] | 0
Totals >> | 114.9 | 30.7 |  | 147 |  | Total Actual Hours Worked >> | [8 empty] | 24.3 | 1 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ^ | ^ | ^ | ^ | ^ | Cumulative Actual Hours (AC) >> | [8 empty] | 24.3 | 25.3 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 | 30.3 |  | 28.3
| Total Estimated Hours Remaining | Actual Hours So Far | Actual Completion Week | Total Hours Originally Estimated | Planned Completion Week | Estimated Hours Remaining (copy each week from total in column E) >> | [7 empty] | 147 | 2018-01-26: 66.2; 2018-02-02: 66.2; 2018-02-09: 114.9
| (copy to the right at the end of each week) | Should match Cumulative Actual Hours (AC) | (fill in when the task is complete) | Should match Cumulative Plan (PV) | [8 empty] | Week Number >> |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
[6 empty] | Hours Earned This Week (enter each week) >> | [8 empty] | 66.2 1: 23.5; 66.2 2: 0; 114.9 3: 4
[6 empty] | Cumulative Hours Earned (EV) >> | [8 empty] | 23.5 | 23.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5 | 27.5
[13 empty] | CPI >> |  | 0.96708 | 0.92885 | 0.90759 | 0.90759 | 0.90759 | 0.90759 | 0.90759 | 0.90759 | 0.90759 | 0.90759 | 0.90759 | 0.90759 | 0.90759 | 0.90759
[13 empty] | SPI >> |  | 2.2381 | 1.119 | 0.87302 | 0.65476 | 0.52381 | 0.43651 | 0.37415 | 0.32738 | 0.29101 | 0.2619 | 0.2381 | 0.21825 | 0.20147 | 0.18707
[15 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2018 Spring